PROJECT SCHEDULE

{{JOB NAME}} — {{GC NAME}} — {{SITE CITY, STATE}}

INTERNAL DOCUMENT — GCC EYES ONLY Contains internal cost rates, margin analysis, and strategy. Never attach to a proposal, quote, or email to a GC, Owner, or Subcontractor.

SCHEDULE SNAPSHOT

| Metric | Value |
| --- | --- |
| NTP / Mobilization Date | {{}} |
| Substantial Completion Target | {{}} |
| Duration (calendar weeks) | {{}} |
| Duration (working weeks) | {{}} |
| Crew Size Peak | {{}} personnel (1 F + {{}} L) |
| Crew Size Average | {{}} personnel |
| Work Hours (baseline) | M-F, 7:00 AM - 3:30 PM |
| Holidays / Blackouts | {{list}} |
| Shift Modes | Standard only (after-hours DEDUCT available if surplus capacity) |

1.  Phase Milestones

| # | Phase | Start | Finish | Duration | % of Base Bid |
| --- | --- | --- | --- | --- | --- |
| P1 | Mobilization & submittals | {{}} | {{}} | {{days}} | 10% |
| P2 | Rough-in (pathway, boxes, backboxes) | {{}} | {{}} | {{days}} | 30% |
| P3 | Cable pull & rack equipment | {{}} | {{}} | {{days}} | 30% |
| P4 | Terminations, dressing, labels, testing | {{}} | {{}} | {{days}} | 20% |
| P5 | Punch, as-builts, closeout, warranty registration | {{}} | {{}} | {{days}} | 10% |

Phase percentages align with Bid Proposal §6 Milestones (10/30/30/20/10). Pay application triggers on phase substantial completion.

2.  Gantt — Week-by-Week

Gantt grid populated per job. Template shows structure only. Each '█' = active week; '▒' = partial/ramp week.

| Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P1 Mobilize | █ | · | · | · | · | · | · | · | · | · |
| P2 Rough-in | · | █ | █ | █ | · | · | · | · | · | · |
| P3 Cable pull | · | · | · | █ | █ | █ | · | · | · | · |
| P4 Terminate / test | · | · | · | · | · | █ | █ | █ | · | · |
| P5 Punch / close | · | · | · | · | · | · | · | · | █ | █ |

3.  Crew Loading

| Phase | Duration (weeks) | Crew | Hours / Week | Total Hours |
| --- | --- | --- | --- | --- |
| P1 Mobilization | {{}} | 1 F + 1 L | 80 | {{}} |
| P2 Rough-in | {{}} | 1 F + 2 L | 120 | {{}} |
| P3 Cable pull | {{}} | 1 F + 3 L | 160 | {{}} |
| P4 Terminate / test | {{}} | 1 F + 2 L | 120 | {{}} |
| P5 Punch / close | {{}} | 1 F + 1 L | 80 | {{}} |
| MOBS (ongoing) | {{}} | 1 F only | 4/wk | {{}} |
| TOTAL | {{}} | — | — | {{}} |

Minimum on-site = 2 personnel at all times (safety baseline). Foreman ratio max 1:3. Blended cost rate: 2-crew = $52.50/hr; 3-crew = $48.33/hr; 4-crew = $46.25/hr. Billed rate = $100/hr flat regardless of composition.

4.  Dependencies & Assumptions

Predecessor Dependencies (by others)

Pathway (EMT, cable tray, J-hook) installed by Electrical Contractor before GCC cable pull (P3). See Bid Proposal §7.A.

Ceiling grid + above-ceiling pathway access complete before P3.

MDF / IDF rooms climate-controlled + locked before P3 rack install.

Power whips to all racks energized before P4 terminations (NVR, switches, APs).

Building permits + low-voltage permit in-place — GCC does not pull (Bid Proposal §7.J).

Working Assumptions

Single-shift daytime work unless GC requests DEDUCT alt for labor-surplus weekend/after-hours.

No stacked trades in same work area during cable pull phase.

GCC has parking + material staging within 200 ft of MDF / loading dock.

Elevator use: freight elevator available during working hours; standard passenger elevator off-hours only.

Schedule Modifications

If NTP delayed by >10 business days from current base date, GCC re-evaluates resource availability and may issue mobilization Change Order.

Weather blackout on outdoor work — GCC not responsible for delay.

Holidays observed (not worked): New Year's Day, Memorial Day, July 4, Labor Day, Thanksgiving + day after, Christmas Eve + Day.